## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Ravi | 2026-07-08 | Upload card file picker blocked by decorative overlay element | Sprint 1 | Ravi | User Interface | Replaced overlay interaction with explicit click handler and hidden file input | 2026-07-11 | Closed | Retested drag & drop and file picker flows successfully
2 | Ravi | 2026-07-17 | Missing export functionality for analysis results in web portal view | Sprint 2 | Ravi | Feature Defect | Implemented Markdown/PDF report generator connected to download action button | 2026-07-19 | Closed | Verified export generation for Python and Java code scans
3 | Ravi | 2026-07-20 | UI visual layout flat, missing overview cards and clear action buttons | Sprint 3 | Ravi | UI / UX Bug | Redesigned hero section, added severity cards, badges, and improved action button contrast | 2026-07-22 | Closed | Enhanced visual hierarchy without breaking build/lint checks
4 | Ravi | 2026-07-23 | Code Analysis and Security agents executed in isolation without unified web endpoint | Sprint 4 | Ravi | API Integration Defect | Connected UnifiedOrchestrator to /analyze API endpoint to run agents in parallel | 2026-07-24 | Closed | Combined static analysis and security findings into single payload
5 | Ravi | 2026-07-25 | RAG vector store paths contained hardcoded machine-specific local directories | Sprint 5 | Ravi | Configuration Defect | Refactored vector store path resolution to read from environment variables with relative fallbacks | 2026-07-25 | Closed | Ensured portable execution across local and staging environments
6 | Ravi | 2026-07-27 | Missing ANTHROPIC_API_KEY caused unhandled exception in analysis pipeline | Sprint 6 | Ravi | Logical | Added honest LLM scan status flag (disabled/ok/error) to fallback gracefully without crashing | 2026-07-28 | Closed | Verified via UT-08; pipeline proceeds with static rule results when key is missing
7 | Ravi | 2026-07-29 | Inconsistent finding schema between Code Analysis and Remediation agents across Python/Java | Sprint 8 | Ravi | Standards | Standardized JSON finding schema across all agent parsers before downstream integration | 2026-07-30 | Closed | Resolved schema mismatch for Remediation and PR Summary agent consumption
8 | Ravi | 2026-08-02 | Conversational Assistant returned generic OWASP advice ignoring current scan findings | Sprint 9 | Ravi | RAG Retrieval Defect | Injected active findings list and code health score into RAG prompt context window | 2026-08-04 | Closed | Verified grounded chatbot answers using current session context (UT-16)
9 | Ravi | 2026-08-05 | Lack of text search (Find) and Replace feature in code submission view | Sprint 14 | Ravi | UI / Usability Bug | Integrated Monaco Editor Find/Replace action controllers | 2026-08-06 | Closed | Added search highlighting and instant code string replacement capabilities
10 | Ravi | 2026-08-07 | Duplicate findings generated when regex pattern detector and LLM scan flag same line | Sprint 15 | Ravi | Deduplication Bug | Integrated Monaco Editor Find/Replace action controllers | 2026-08-08 | Closed | Verified via UT-09; duplicate findings eliminated successfully

## Sheet2
Logical
User Interface
Maintainability
Standards
Others