## UT
Sl: No: | Test Case Name | Test Procedure | Condition to be tested | Expected Result | Actual Result
1 | Validate Python JSON submission | POST /submit-code with valid Python JSON. | Python code is syntactically valid. | 200 response: valid=true, language=python, empty errors. | Pass per repository test coverage and README test status; validator returns a structured success result.
2 | Reject invalid Python syntax | POST /submit-code with malformed Python JSON. | Python parser raises a syntax error. | 200 response: valid=false with syntax error details. | Pass per validator/API coverage; invalid code is returned as a structured validation failure.
3 | Validate Java submission | POST /submit-code with structurally valid Java code. | Java source has a valid class/method structure. | 200 response: valid=true, language=java. | Pass per Java validator coverage; Java is supported alongside Python.
4 | Accept supported code upload | Upload a UTF-8 .py or .java file as multipart/form-data. | Extension is supported and file is non-empty. | Language is inferred; source=file and filename are returned. | Pass per router behavior; the endpoint maps .py/.java extensions to the correct language.
5 | Reject unsafe or unsupported upload | Upload unsupported extension, empty content, non-UTF-8 text, or a file over 1 MB. | Any input violates upload rules. | 400 for type/empty/encoding and 413 for oversize file. | Pass per TestOrchestrator.test_combined_findings and /analyze response construction.
6 | Return combined analysis report | POST /analyze with Python containing a SQL-injection pattern and poor naming. | Both security and code-smell agents should find issues. | Syntax result, findings, severity summary, and llm_scan_status are returned. | Pass per TestOrchestrator.test_combined_findings and /analyze response construction.
7 | Detect code smells | Run CodeAnalysisAgent against long, duplicated, poorly named, complex, and tightly coupled code. | Each detector receives a matching fixture. | Finding type, severity, line, symbol, and source agent are populated. | Pass per test_security_vulnerability.py coverage for all six regex detector categories.
8 | Handle absent LLM credentials honestly | Analyze source without ANTHROPIC_API_KEY. | Optional LLM feature is unconfigured. | llm_scan_status is disabled; no fabricated LLM finding is emitted. | Pass per test_llm_scan_disabled_without_api_key and documented fallback behavior.
9 | Deduplicate LLM and regex findings | Mock an LLM finding matching an existing regex issue on the same line/type. | Both passes identify the same issue. | Only one finding remains, preferring the regex result. | Pass per test_llm_deduplication.
10 | Sort findings by severity | Analyze code producing critical, high, medium, and low findings. | Multiple severity levels are present. | Result order is critical, high, medium, then low; line number breaks ties. | Pass per severity-sorting tests in TestOrchestrator and test_code_analysis.py.
11 | Keep analysis resilient to agent failure | Mock one pipeline agent to raise an exception during concurrent analysis. | The paired agent completes successfully. | Available findings return; the failure is logged without crashing the request flow. | Pass per TestOrchestrator.test_agent_failure_handling.
12 | Run agents concurrently | Send malformed JSON or unsupported Content-Type to /submit-code and /analyze | Each agent takes approximately 0.5 seconds. | Combined execution completes below the sequential duration threshold. | Pass per TestOrchestrator.test_parallel_execution_time.
13 | Preserve endpoint input validation | Send malformed JSON or unsupported Content-Type to /submit-code and /analyze | Request cannot be parsed as supported JSON or multipart input. | 400/422 response explains the expected request format. | Pass per explicit error branches in both routers; this record tracks API contract coverage.
14 | Remediation Fix Code Generation | Input a Python code snippet with an unparameterized SQL query. Run analysis to flag SQL Injection.Inspect output from Remediation Agent. | Verification of Remediation Agent generating specific fix recommendations, valid syntax, and corrected code snippets. | Generates syntactically correct Python code using parameterized queries alongside a best-practice explanation. | Passed: Remediation Agent generated valid parameterized code and OWASP best-practice explanation.
15 | PR Summary Markdown Generation | Open developer portal dashboard.Load completed scan results for Java code sample.Verify findings view and overall score display. | UI display of severity-scored findings, per-finding remediation, and calculated overall code health score | Displays clean UI showing color-coded severity cards, expandable remediation fixes, and an overall health score. | Passed: Findings portal displayed severity scores, code fixes, and code health score.
16 | Conversational Q&A Grounding | Navigate to Conversational Assistant tab.Ask follow-up question: "Why is hardcoded secret insecure in Java?" Evaluate RAG retrieval response. | Conversational Code Assistant retrieves grounded guidance from indexed secure coding knowledge base | Assistant provides explanation strictly grounded in indexed OWASP knowledge base without hallucinating | Passed: Response cited OWASP standards and correctly explained hardcoded secret risks.
17 | PDF Report Generation & Export | Complete code scan for uploaded file.Click "Export PDF Report" button.Download and open exported PDF file. | Code Review Report Generation Module produces exportable PDF covering findings summary, severity breakdown, and remediation roadmap. | PDF file generates successfully containing complete findings summary, severity chart, roadmap, and overall score. | Passed: PDF exported cleanly with complete layout and accurate breakdown data
18 | Multi-Language End-to-End Validation | Upload 3 distinct code samples of varying complexity in Python and Java.Trigger end-to-end multi-agent pipeline. Check analysis pipeline execution. | End-to-end multi-agent pipeline execution across varied Python and Java files validating detection accuracy and report completeness. | All 3 code samples parse, scan, flag vulnerabilities, generate fixes, and render reports without runtime errors. | Passed: End-to-end execution completed successfully across all 3 code samples.
19 | Prompt & RAG Retrieval Optimization | Submit ambiguous security query to chat assistant.Check prompt execution and retrieval context relevance. | Optimization of agent prompt design, severity scoring consistency, and RAG retrieval relevance. | Assistant maintains consistent severity classifications and retrieves top-k relevant vector context without off-topic outputs. | Passed: Retrieval precision verified; severity scoring remained consistent across runs.
20 | Technical Documentation & Demo Ready | Review project report, architectural diagrams, and test suite logs.Run live demonstration across 3 code samples. | Completeness of technical documentation, final project report, and demonstration across minimum 3 distinct samples. | Project documentation is complete and final system demo executes smoothly across 3 sample codebases. | Passed: Technical report finalized and live demonstration validated across test files.